## Slide 1: Project Charcter
Official project name: Electric Remote System
Project sponsor: TCI Egypt For Home Automation Co , Ministry of electricity&renewable energy.
Project manager: Mostafa Samy
Purpose of the project: To solve the problem of management and controlling Electricity outside home
Business case
Electric Remote System app is designed to control electricity of houses that use smart systems
, it replaces manual control of electricity that may has danger in some cases like natural disasters and emergency cases . it helps people that has movement issues and injured people who need to rest .
Saving electricity by turning it off if the owner of house forget electricity on while he is outside.

## Slide 2
Project scope
1-The App will help user to know electric3ity that turn on/off.
2-The App will help user to turn on or turn off electricity.
3- The App will calculate the usage of electricity in the house and show it as a graph .
4- the app help user to rationalize of electricity consumption(ترشيد استهلاك الكهرباء ( .
Project milestones
- Requirements review : Requirements specifications are complete, correct, approved and suitable. 14/1/2022
- Critical design review: Detailed designs fully implement the system architecture,
are approved and are suitable for input into the development of code. By 15/2/2022
- System test review : The software product has passed system testing and is suitable for input into acceptance testing.
by 15/3/2022
- Product operational: The software is in use in its target operational environment.by 25/3/2022
Project resources
Staff : 1 android developers ,1 IOS developers , 1 back end developer , 1 electric engineer
Hardware : 4 laptops , 2 server
Software : Software licenses (Editors : phpstorm , ….)
Budget
budget allocated for this project is 500000 L.E

## Slide 3
Constraints
- this project must be delivered within the specified budget .
- This project must be delivered on 1/4/2022.
- Any laptops or computers needed must be bought from dell company
Assumptions (required event must be occur every fixed period)
- will get all resources required.
- All important stakeholders will come to the specified meetings.
- All team members continue to the end of the project
High level risks
- Inaccurate estimates
- Scope creep : uncontrolled changes and continuous growth of the scope.or scope is ill defined
- Project team misunderstand requirements
- Loss of key personnel
- Customer will not accept the software as delivered even though it meets all specifications
- Selected technology is a poor match to the problem or customer
- Project key success criteria not clearly defined to verify the successful completion of each project phase.
- Projects within the program often need the same resources at the same time

## Slide 4: work breakdown Structure (WBS)

## Slide 5
1. Electric Remote System
1.1 Requirements
1.1.1 Place
1.1.2 Hardware
1.1.3 Software
1.2.1 Develop App
1.2.1.1 Design
1.2.1.2 Coding
1.2.1.3 Debugging
1.2.2 Control System
1.2.2.1 Subsystem control
1.2.2.2 Sensors
1.2.2.3 integrate with Electricity devices
1.2.3 Test
1.2.2.4 Link app with Bank System
1.2.2.5 Link app with Ministry of Energy System
1.2.3.1 Check
Payment
1.2.3.2 Check integration
1.2.3.3 Test controlling Electricity
1.2 Develop & Test
1.3 Documentation
1.3.1 Project Proposal
1.3.2 Technical report
1.3.3 Project Report
1.3.4 Final Project presentation

## Slide 6: Project network

## Slide 7
Project Network ------------------------------------------------------------------------------------- Activity Description Preceding activity Activity Time A Define Requirements None 7 B Assign Team A 5 C Design Hardware A 20 D Coode Software B 15 E Build And Test Hardware C 40 F Develop Patent Request C 10 G Test Software D 30 H Integrate Systems E,F,G 13

## Slide 8: Project Network
0 | A | 
0 | Define Requirement | 
0 |  | 7
7 | C | 27
0 | Design Hardware | 
7 | 20 | 27
7 | B | 12
30 | Assign Team | 
37 | 5 | 42
12 | D | 27
30 | Coode Software | 
42 | 15 | 57
27 | E | 67
0 | Build And Test Hardware | 
27 | 40 | 67
27 | F | 37
30 | Test Software | 
57 | 10 | 67
67 | H | 84
0 | Integrate Systems | 
67 | 17 | 84
27 | G | 57
10 | Develop Patent Request | 
37 | 30 | 67

## Slide 9: Resource-Constrained project

## Slide 10: Resource Scheduled Network
0 | A | 2
0 | 2P | 0
0 | 2 | 2
2 | C | 6
0 | 2P | 0
2 | 4 | 6
2 | B | 4
3 | 1P | 3
5 | 2 | 7
4 | D | 7
3 | 2P | 3
7 | 3 | 10
6 | E | 13
0 | 2P | 0
6 | 7 | 13
7 | F | 10
3 | 1P | 3
10 | 3 | 13
13 | H | 15
0 | 3P | 0
13 | 2 | 15
6 | G | 11
2 | 2P | 2
8 | 5 | 13

## Slide 11
A | 2 | 2 | 0 | 2 | 0 | 2 | 2 |  |  |  |  |  |  |  |  |  | 
B | 2 | 2 | 2 | 7 | 3 |  |  | 2 | 2 |  |  |  |  |  |  |  | 
C | 2 | 4 | 2 | 6 | 0 |  |  | 2 | 2 | 2 | 2 |  |  |  |  |  | 
D | 2 | 3 | 4 | 10 | 3 |  |  |  |  | 2 | 2 | 2 |  |  |  |  | 
E | 2 | 7 | 6 | 13 | 0 |  |  |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2
F | 2 | 3 | 7 | 13 | 3 |  |  |  |  |  |  |  | 2 | 2 | 2 |  | 
G | 2 | 5 | 6 | 13 | 2 |  |  |  |  |  |  | X | X | X | X | 2 | 2
H | 2 | 2 | 13 | 15 | 0 |  |  |  |  |  |  |  |  |  |  |  | 
Total Resource load |  |  |  |  |  | 2 P | 2P | 4P | 4P | 4P | 4P | 4P | 4P | 4P | 4P | 4P | 4P
Resource Available |  |  |  |  |  | 4P | 4 P | 4 P | 4 P | 4 P | 4 P | 4 P | 4P | 4P | 4P | 4P | 4P
Id Res Dur Es Lf Sl 0 1 2 3 4 5 6 7 8 9 10 11 12

## Slide 12: Time Phase Budget

## Slide 13
A | 2 | Define Requirements | 2 | 1 | 1 |  |  |  |  |  |  |  |  |  | 
B | 2 | Assign Team | 2 |  |  | 1 | 1 |  |  |  |  |  |  |  | 
C | 4 | Design Hardware | 6 |  |  | 3 |  |  | 3 |  |  |  |  |  | 
D | 3 | Coode Software | 8 |  |  |  |  | 2 | 2 | 4 |  |  |  |  | 
E | 7 | Build And Test Hardware | 5 |  |  |  |  |  |  | 2 |  | 1 |  | 1 | 
F | 3 | Develop Patent Request | 3 |  |  |  |  |  |  |  | 1 | 1 | 1 |  | 
G | 5 | Test Software | 2 |  |  |  |  |  |  | 1 |  |  |  | 1 | 
H | 2 | Integrate Systems | 3 |  |  |  |  |  |  |  |  |  | 1 | 1 | 1
Week total |  |  | 31 | 1 | 1 | 4 | 1 | 2 | 5 | 7 | 1 | 2 | 1 | 2 | 0
Cumulative |  |  |  | 1 | 2 | 6 | 7 | 9 | 14 | 21 | 22 | 24 | 25 | 27 | 27
Id Dur Task Budget 0 1 2 3 4 5 6 7 8 9 10 11 12

## Slide 14: Risk Management

## Slide 15: Risks
Familiarity with application:
The team has familiarity with Home Automation as they did a voice assistant control in turning on/off electricity devices.
Risk: Low.
Familiarity with technology:
The team has familiarity with AI technology
As they used in the mentioned project.
Risk: Low.

## Slide 16
Project size:
The project is big therefore the team should have more members and need more time.
Risk: High.
Compatibility:
The app is compatible with the technology of the company. However, the technology should be updated to make the performance better and smoother.
Risk: Medium.

## Slide 17: Thank you